## Progress Tracker
Milestone | Owner | Planned Date | Status | RAG Status | Notes
Kickoff & Stakeholder Alignment | Jordan | Week 1 | Completed | Green | All stakeholders aligned
Finalize RACI & Assign Workstreams | Casey | Week 2 | In Progress | Yellow | Pending approval
Launch Pilot Phase | Drew | Week 3 | Not Started | Red | Resources not confirmed
Evaluate Pilot & Adjust Plan | Taylor | Week 5 | Not Started | Red
Full Rollout | Chris | Week 6 | Not Started | Yellow
Midpoint Review & Optimization | Casey | Week 8 | Not Started | Green
Final Review & Executive Closeout | Jordan | Week 10 | Not Started | Green